## Sheet1
date | discipline | activity_description | status | equipment_tag | location | reported_by
2026-08-30 | Piping | Started erection of XX-101 spool | Started | XX-101 | Area B | Supervisor A
2026-08-30 | Civil | Foundation A1 concrete pouring in progress | In Progress | A1 | Area C | Supervisor B
2026-08-29 | Mechanical | Pump P-101 installation completed | Completed | P-101 | Pump House | Supervisor C
2026-08-30 | Electrical | Cable pulling for substation delayed due to rain | Delayed | SUB-1 | Substation | Supervisor D